## SBL
No. | Status | Priority | Plan man-hours | Task content | developer | Start Date | Actual man-hours
1 | Done | High | 4 | develo meetting | All | 2022-03-01 | 20 | =SUMIF(SBL!D:D,"
2 | Done | High | 4 | develo meetting | All | 2022-03-02 | 3 | =SUMIF(SBL!D:D,"
3 | Done | High | 4 | develo meetting | All | 2022-03-03 | 30 | =SUMIF(SBL!D:D,"
4 | Done | High | 4 | develo meetting | All | 2022-03-16 | 4 | =SUMIF(SBL!D:D,"
5 | ToDo | Middle | 4 | code | Jack | 2022-03-16 | 4
6 | InProgress | High | 2 | test | John | 2022-03-16 | 4
7 | Done | High | 4 | develo meetting | All | 2022-03-17 | 4 | =SUMIF(SBL!D:D,"
8 | ToDo | Middle | 4 | code | Jack | 2022-03-17 | 4
9 | InProgress | High | 2 | test | John | 2022-03-17 | 4
10 | Done | High | 4 | develo meetting | All | 2022-03-18 | 4 | =SUMIF(SBL!D:D,"
11 | ToDo | Middle | 4 | code | Jack | 2022-03-18 | 4
12 | InProgress | High | 2 | test | John | 2022-03-18 | 4
13 | Done | High | 4 | develo meetting | All | 2022-03-19 | 4 | =SUMIF(SBL!D:D,"
14 | ToDo | Middle | 4 | code | Jack | 2022-03-19 | 4
15 | InProgress | High | 2 | test | John | 2022-03-19 | 4

## Sheet3 (hidden)
3
5
アクション
サービス
SQL
画面
DTO
DTO
DTO

## BurnDown
| 2022-03-01 | 2022-03-02 | 2022-03-03 | 2022-03-04 | 2022-03-05 | 2022-03-06 | 2022-03-07 | 2022-03-08 | 2022-03-09 | 2022-03-10 | 2022-03-11 | 2022-03-12 | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-18 | 2022-03-19 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31
| Tue | Wed | Thu | Fri | Sta | Sun | Mon | Tue | Wed | Thu | Fri | Sta | Sun | Mon | Tue | Wed | Thu | Fri | Sta | Sun | Mon | Tue | Wed | Thu | Fri | Sta | Sun | Mon | Tue | Wed | Thu
Jack | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5
John | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5
Dan | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 5 | 5 | 5 | 5
Plan | 15 | 30 | 45 | 60 | 60 | 60 | 75 | 90 | 105 | 120 | 135 | 135 | 135 | 150 | 165 | 180 | 195 | 210 | 210 | 210 | 225 | 240 | 255 | 270 | 285 | 285 | 285 | 300 | 315 | 330 | 345
Actual | 20 | 23 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 53 | 57 | 61 | 65 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69 | 69